## Cover Page
SOFTWARE TEST PLAN
Comprehensive Test Planning Template — IEEE 829 Aligned
Project Name: |  |  |  | Confidentiality: | Internal
Application / System: |  |  |  | Document Type: | Test Plan
Version: |  |  |  | Phase:
Test Plan ID: | TP-001 |  |  | Release / Sprint:
Prepared By: |  |  |  | Environment:
Reviewed By: |  |  |  | QA Lead:
Approved By: |  |  |  | Dev Lead:
Date Created: |  |  |  | Product Owner:
Last Updated: |  |  |  | Stakeholders:
Status: | Draft |  |  | Review Deadline:
▸ REVISION HISTORY
Version | Date | Author | Change Description | Reviewed By | Approved By | Status | Notes
1.0 |  |  | Initial draft created |  |  | Draft
1.1 |  |  | Updated scope and test cases |  |  | In Review
2.0 |  |  | Final version after UAT sign-off |  |  | Approved
▸ SIGN-OFF
Role | Name | Signature | Date | Comments
QA Lead
Project Manager
Product Owner
Development Lead
Client Representative

## Test Plan Overview
TEST PLAN OVERVIEW
▸ 1. INTRODUCTION & PURPOSE
This Test Plan defines the strategy, scope, resources, schedule, and approach for testing [Project Name]. It establishes the framework within which testing will be planned and performed to ensure the delivered software meets all specified requirements.
▸ 2. TEST OBJECTIVES
• Verify all functional requirements are correctly implemented. • Validate non-functional requirements (performance, security, usability). • Identify and document defects before production release. • Ensure system stability across supported platforms and environments. • Provide confidence to stakeholders that the product is release-ready.
▸ 3. SCOPE — IN SCOPE
• Functional testing of all modules listed in the BRD/SRS. • Integration testing between system components. • Regression testing after each bug fix. • Performance and load testing for critical endpoints. • Security testing (authentication, authorization, data protection). • UAT support and defect triage.
▸ 4. SCOPE — OUT OF SCOPE
• Third-party service internal logic (payment gateways, SMS providers). • Infrastructure provisioning and cloud deployment pipelines. • Data migration scripts (covered by separate Data Migration Test Plan). • Hardware compatibility testing beyond specified device matrix.
▸ 5. TEST APPROACH & STRATEGY
Testing will follow an Agile iterative approach aligned to sprint cycles. Unit tests are owned by developers; QA owns integration, system, regression, and UAT coordination. Automation will be applied to regression suites using [Tool]. Manual testing covers exploratory, UX, and ad-hoc scenarios. Risk-based testing prioritizes critical and high-priority requirements.
▸ 6. ASSUMPTIONS & DEPENDENCIES
• Test environments will be provisioned and stable before sprint testing begins. • Requirements and design documents are baselined before test case authoring. • Development team provides deployment builds by the agreed cut-off time. • Access credentials and test data will be provided by the Dev team. • Defects will be triaged within 24 hours of reporting.
▸ 7. RISKS & MITIGATION
Risk 1: Late requirement changes → Mitigation: Change freeze 1 week before testing. Risk 2: Unstable test environment → Mitigation: Dedicated QA environment with daily health check. Risk 3: Resource unavailability → Mitigation: Cross-trained backup QA resource identified. Risk 4: Scope creep → Mitigation: Formal change request process enforced.
▸ 8. ENTRY & EXIT CRITERIA
ENTRY: All test cases reviewed and approved; test environment deployed; build smoke test passed; test data prepared. EXIT: 100% of High/Critical test cases executed; 0 open Critical defects; 0 open High defects; UAT sign-off received; test summary report approved.

## Schedule & Resources
TEST SCHEDULE & RESOURCE PLAN
▸ KEY TESTING MILESTONES
Milestone | Phase | Planned Start | Planned End | Actual Start | Actual End | Owner | Status | % Complete | Notes
Test Plan Created & Approved | Planning |  |  |  |  | QA Lead | Completed | 100%
Test Cases Authored & Reviewed | Planning |  |  |  |  | QA Team | In Progress | 75%
Test Environment Setup | Setup |  |  |  |  | DevOps | Pending | 0%
Test Data Preparation | Setup |  |  |  |  | QA Team | Pending | 0%
Smoke / Sanity Testing | Sprint 1 |  |  |  |  | QA Lead | Not Started | 0%
Functional Testing — Sprint 1 | Sprint 1 |  |  |  |  | QA Team | Not Started | 0%
Integration Testing | Sprint 2 |  |  |  |  | QA Team | Not Started | 0%
Regression Testing | Sprint 2 |  |  |  |  | QA Team | Not Started | 0%
Performance Testing | Sprint 3 |  |  |  |  | Perf Engr | Not Started | 0%
Security Testing | Sprint 3 |  |  |  |  | Sec Engr | Not Started | 0%
UAT Execution | UAT |  |  |  |  | QA Lead | Not Started | 0%
Defect Closure & Sign-off | Closure |  |  |  |  | QA Lead | Not Started | 0%
Test Summary Report | Closure |  |  |  |  | QA Lead | Not Started | 0%
▸ RESOURCE PLAN
Resource Name | Role | Skills / Tools | Allocation % | Phases Involved | Start Date | End Date | Notes
| QA Lead | Test Management, JIRA, Postman, Selenium | 100% | All phases
| QA Engineer 1 | Manual Testing, JIRA, Postman | 100% | Sprint 1-3, UAT
| QA Engineer 2 | Automation, Cypress / Playwright | 75% | Sprint 2-3, Regression
| Perf Engineer | JMeter / k6, Grafana | 50% | Sprint 3
| Security Engr | OWASP ZAP, Burp Suite | 25% | Sprint 3
| Business Analyst | Requirements, UAT coordination | 25% | Planning, UAT
| Dev Lead | Code review, defect fixes | 20% | All phases
▸ TEST ENVIRONMENT MATRIX
Environment | Purpose | URL / Host | OS | Browser / Client | DB Version | Deployed By | Refresh Frequency | Status | Notes
DEV | Unit/Dev testing | dev.app.internal | Ubuntu 22 | Chrome latest | PG 15 | DevOps | On each commit | Active
QA | Functional/Integration | qa.app.internal | Ubuntu 22 | Chrome + Firefox | PG 15 | DevOps | Daily build | Active
STAGING | Regression/UAT | staging.app.internal | Ubuntu 22 | All browsers | PG 15 | DevOps | Sprint release | Active
PERF | Performance/Load testing | perf.app.internal | Ubuntu 22 | Headless Chrome | PG 15 | DevOps | On demand | Pending
PROD | Production — do NOT test | app.company.com | Ubuntu 22 | N/A | PG 15 | DevOps | N/A | Live | Read-only

## Test Cases
TEST CASE REPOSITORY
▸ All test cases are tracked here. Link to RTM via REQ ID.
TC ID | REQ ID | Module | Test Case Title | Test Type | Priority | Preconditions | Test Steps | Expected Result | Actual Result | Status | Pass/Fail | Executed By | Exec Date | Defect ID
TC-001 | REQ-001 | Auth | User Registration — Valid Email & Password | Functional | High | App is running; user is not registered | 1. Navigate to /register 2. Enter valid email 3. Enter strong password 4. Click Register | Account created; confirmation email sent |  | Passed | Pass
TC-002 | REQ-001 | Auth | User Registration — Duplicate Email | Functional | High | Existing account with same email | 1. Navigate to /register 2. Enter duplicate email 3. Submit | Error: 'Email already in use' |  | Passed | Pass
TC-003 | REQ-001 | Auth | User Registration — Invalid Email Format | Functional | Medium | None | 1. Enter invalid email (e.g., user@) 2. Submit form | Inline validation error displayed immediately |  | Passed | Pass
TC-004 | REQ-002 | Auth | Email Verification Link Sent | Functional | High | New account registered | 1. Complete registration 2. Check email inbox | Verification email received within 2 minutes |  | In Progress
TC-005 | REQ-003 | Auth | Password Reset — Valid Token | Functional | High | Registered user, valid token | 1. Click Forgot Password 2. Enter email 3. Open link in email 4. Enter new password | Password changed; redirect to login |  | Failed | Fail |  |  | DEF-007
TC-006 | REQ-008 | Auth | Password Hashing — bcrypt Verification | Security | Critical | DB access available | 1. Register user 2. Query DB password column | Password is bcrypt hash (starts with $2b$12$) |  | Passed | Pass
TC-007 | REQ-009 | Infra | HTTPS Enforcement on All Endpoints | Security | Critical | SSL cert configured | 1. Access any endpoint via HTTP 2. Observe redirect | 301/302 redirect to HTTPS; TLS 1.2+ negotiated |  | Passed | Pass
TC-008 | REQ-005 | Infra | Load Test — 1000 Concurrent Users | Performance | High | Perf environment up, JMeter script ready | 1. Run JMeter plan with 1000 threads 2. Monitor response times | 95th percentile response < 1s; 0 errors |  | In Progress
TC-009 | REQ-011 | Dashboard | Dashboard Metrics Visible Without Scrolling | UI | Medium | User logged in; 1080p resolution | 1. Log in 2. Navigate to dashboard 3. Observe screen | All KPI cards visible without vertical scroll |  | Not Run
TC-010 | REQ-013 | Payments | Stripe Payment — Successful Charge | Integration | High | Stripe test keys configured | 1. Add item to cart 2. Enter test card 4242 4242 4242 4242 3. Submit | Payment confirmed; order created; webhook received |  | Not Run
TC-011 | REQ-014 | Notifications | SendGrid — Transactional Email Delivery | Integration | High | SendGrid API key set | 1. Trigger order confirmation 2. Check inbox | Email received within 60 seconds |  | Passed | Pass
TC-012 | REQ-015 | User Mgmt | GDPR — Data Export Request | Compliance | Critical | Logged-in user with data | 1. Go to Privacy Settings 2. Request data export 3. Await email | ZIP file emailed within 72 hours; includes all user data |  | Not Run

## Defect Log
DEFECT LOG
▸ Log all defects here. Link to Test Case and Requirement IDs.
Defect ID | TC ID | REQ ID | Title | Module | Severity | Priority | Status | Reported By | Reported Date | Assigned To | Target Fix Date | Fixed Date | Root Cause | Remarks
DEF-001 | TC-005 | REQ-003 | Password reset token not expiring after use | Auth | High | High | Open | QA Eng 1 |  | Dev Lead |  |  | Logic error in token invalidation | Reproduces 100%
DEF-002 | TC-008 | REQ-005 | Response time spikes to 4s under 800 concurrent users | Infra | Critical | High | In Progress | Perf Engr |  | Backend Dev |  |  | DB query missing index | Index added in PR #88
DEF-003 | TC-009 | REQ-011 | Dashboard KPI card overlaps on 1080p in Firefox | Dashboard | Medium | Medium | Open | QA Eng 2 |  | Frontend Dev |  |  | CSS flex overflow bug | Only on Firefox 121+
DEF-004 | TC-010 | REQ-013 | Stripe webhook not received on local dev tunnel | Payments | High | High | Closed | QA Eng 1 |  | Dev Lead |  |  | ngrok tunnel timeout | Fixed by increasing webhook timeout
DEF-005 | TC-012 | REQ-015 | GDPR export missing address field in ZIP | User Mgmt | Critical | High | Open | QA Lead |  | Dev Lead |  |  | Serializer excludes address | Blocked — awaiting DB schema update

## Metrics Dashboard
TEST METRICS DASHBOARD
Auto-calculated from Test Cases and Defect Log sheets
Total Test Cases | Passed | Failed | Not Run | In Progress | Total Defects | Open Defects | Critical Defects | Closed Defects | Pass Rate %
12 | 6 | 1 | 3 | 2 | 5 | 3 | 2 | 1 | 50%
▸ Test Cases by Test Type
Test Type | Total | Passed | Failed | Not Run
Functional | 5 | 3 | 1 | 0
Security | 2 | 2 | 0 | 0
Performance | 1 | 0 | 0 | 0
Integration | 2 | 1 | 0 | 1
UI | 1 | 0 | 0 | 1
Compliance | 1 | 0 | 0 | 1
▸ Defects by Severity & Status
Severity | Total | Open | In Progress | Closed
Critical | 2 | 1 | 1 | 0
High | 2 | 1 | 0 | 1
Medium | 1 | 1 | 0 | 0
Low | 0 | 0 | 0 | 0

## Test Summary Report
TEST SUMMARY REPORT
▸ EXECUTIVE SUMMARY
Provide a 3-5 sentence executive summary of the overall test cycle. Include what was tested, key outcomes, go/no-go recommendation, and any critical open risks.
▸ TEST EXECUTION SUMMARY
Sprint/Cycle: ___ ¦ Test Period: ___ to ___ Total TCs: ___ Executed: ___ Passed: ___ Failed: ___ Blocked: ___ Not Run: ___ Pass Rate: ___% ¦ Defect Detection Efficiency: ___%
▸ DEFECT SUMMARY
Total Defects Raised: ___ Critical: ___ High: ___ Medium: ___ Low: ___ Open: ___ In Progress: ___ Closed: ___ Deferred: ___ Defect Removal Efficiency (DRE): ___%
▸ KEY FINDINGS & OBSERVATIONS
1. [Finding 1 — e.g., Auth module 100% pass rate; production-ready] 2. [Finding 2 — e.g., Performance degrades above 800 users; mitigation planned] 3. [Finding 3 — e.g., GDPR export feature incomplete; deferred to v1.1] 4. [Additional findings as needed]
▸ RISKS CARRIED FORWARD
Risk 1: [Description] — Severity: [High/Med/Low] — Owner: [Name] — Plan: [Mitigation] Risk 2: [Description] — Severity: [High/Med/Low] — Owner: [Name] — Plan: [Mitigation]
▸ RECOMMENDATIONS
1. [Recommendation 1 — e.g., Do not release until DEF-005 GDPR defect is resolved] 2. [Recommendation 2 — e.g., Schedule performance optimization sprint before scaling] 3. [Recommendation 3 — e.g., Add automated regression suite for Auth module]
▸ GO / NO-GO RECOMMENDATION
☐ GO — Product meets all exit criteria. Approved for release. ☐ CONDITIONAL GO — Product released with known issues; risk accepted by stakeholders. ☐ NO-GO — Critical defects unresolved. Release not recommended.
▸ LESSONS LEARNED
What went well: • [Item 1] • [Item 2] What to improve: • [Item 1] • [Item 2] Actions for next cycle: • [Action 1] — Owner: ___ — Due: ___