## RTM
REQUIREMENT TRACEABILITY MATRIX (RTM)
Project Name: ___________________________ Version: _______ Date: ___________ Prepared By: ___________________________
▸ TRACEABILITY MATRIX
REQ ID | Category | Requirement Description | Priority | Source | Status | Design Doc Ref | Module / Component | Test Case ID | Test Type | Test Status | Build / Sprint | UAT Case ID | UAT Status | Defect ID | Remarks
REQ-001 | Functional | The system shall allow users to register with a valid email address and password. | High | BRD §2.1 | Approved | DD-001 | Auth Module | TC-001 | Integration | Passed | Sprint 1 | UAT-001 | Passed |  | Login flow verified
REQ-002 | Functional | The system shall send an email verification link upon successful registration. | High | BRD §2.1 | Approved | DD-001 | Auth Module | TC-002 | System | Passed | Sprint 1 | UAT-002 | Passed
REQ-003 | Functional | Users shall be able to reset their password via a secure token link. | High | BRD §2.2 | Approved | DD-002 | Auth Module | TC-003 | System | Failed | Sprint 2 | UAT-003 | In Progress | DEF-007 | Token expiry issue logged
REQ-004 | Functional | The system shall support role-based access control (RBAC) with at least 3 roles. | High | BRD §3.1 | In Review | DD-003 | Auth Module | TC-010 | Unit | Not Run | Sprint 3 |  | Not Started
REQ-005 | Non-Functional | The system shall handle 1,000 concurrent users without performance degradation. | Medium | NFR §1.1 | Approved | DD-010 | Infrastructure | TC-020 | Performance | In Progress | Sprint 2 |  | Not Started |  | Load test ongoing
REQ-006 | Non-Functional | All API responses shall be returned within 300 ms under normal load. | High | NFR §1.2 | Approved | DD-010 | Infrastructure | TC-021 | Performance | Not Run | Sprint 3 |  | Not Started
REQ-007 | Non-Functional | The application shall achieve 99.9% uptime SLA per month. | High | NFR §2.1 | Approved | DD-011 | Infrastructure | TC-022 | Reliability | Not Run | Sprint 4 |  | Not Started
REQ-008 | Security | All passwords shall be hashed using bcrypt with a minimum cost factor of 12. | Critical | SEC §1.1 | Approved | DD-020 | Auth Module | TC-030 | Security | Passed | Sprint 1 | UAT-010 | Passed
REQ-009 | Security | The system shall enforce HTTPS on all endpoints (TLS 1.2+). | Critical | SEC §1.2 | Approved | DD-020 | Infrastructure | TC-031 | Security | Passed | Sprint 1 | UAT-011 | Passed
REQ-010 | Security | Session tokens shall expire after 30 minutes of inactivity. | High | SEC §2.1 | Approved | DD-021 | Auth Module | TC-032 | Security | Failed | Sprint 2 |  | Not Started | DEF-012 | Session not invalidated on mobile
REQ-011 | UI/UX | The dashboard shall display key metrics on a single screen without scrolling on 1080p displays. | Medium | UX §1.1 | In Review | DD-030 | Dashboard | TC-040 | UI | Not Run | Sprint 3 |  | Not Started |  | Wireframe under revision
REQ-012 | UI/UX | All form fields shall display inline validation messages within 200 ms of input. | Medium | UX §1.2 | Approved | DD-031 | UI Components | TC-041 | UI | In Progress | Sprint 2 |  | Not Started
REQ-013 | Integration | The system shall integrate with Stripe for payment processing. | High | BRD §5.1 | Approved | DD-040 | Payments | TC-050 | Integration | In Progress | Sprint 3 |  | Not Started |  | Webhook listener in dev
REQ-014 | Integration | The system shall send transactional emails via SendGrid API. | High | BRD §5.2 | Approved | DD-041 | Notifications | TC-051 | Integration | Passed | Sprint 1 | UAT-020 | Passed
REQ-015 | Compliance | The system shall comply with GDPR — provide data export and deletion on user request. | Critical | LEG §1.1 | In Review | DD-050 | User Management | TC-060 | Compliance | Not Run | Sprint 4 |  | Not Started |  | Legal review pending

## Summary Dashboard
RTM SUMMARY DASHBOARD
Auto-calculated from the RTM sheet · All formulas reference column data in 'RTM'
Total Requirements | Approved | In Review | Tests Passed | Tests Failed | Open Defects
15 | 12 | 3 | 5 | 2 | 2
Requirements by Category |  |  |  | Test Execution Status
Category | Count | % of Total |  | Status | Count | % of Total
Functional | 4 | 33.33% |  | Passed | 5 | 41.67%
Non-Functional | 3 | 25% |  | Failed | 2 | 16.67%
Security | 3 | 25% |  | In Progress | 3 | 25%
UI/UX | 2 | 16.67% |  | Not Run | 5 | 41.67%
Integration | 2 | 16.67%
Compliance | 1 | 8.333%

## Legend & Guide
RTM — LEGEND & FIELD GUIDE
Priority Legend |  | Req. Status Legend
Critical | System-breaking / legal / security — must be done | Draft | Under authoring, not yet reviewed
High | Core business function — required for go-live | In Review | Submitted for stakeholder review
Medium | Important but not blocking release | Approved | Formally signed off — baselined
Low | Nice-to-have / deferred to future sprint | Rejected | Declined — see Remarks for reason
Test Status Legend |  | UAT Status Legend
Passed | All test assertions green | Passed | User accepted — sign-off obtained
Failed | One or more assertions failed | In Progress | User testing underway
In Progress | Test execution in progress | Not Started | UAT phase not reached yet
Not Run | Test not yet started / blocked | Failed | User raised defects — rework required
COLUMN FIELD DESCRIPTIONS
REQ ID | Unique identifier, e.g. REQ-001. Never reuse a deleted ID.
Category | Functional / Non-Functional / Security / UI-UX / Integration / Compliance
Requirement Description | Clear, testable statement using 'shall'. One requirement per row.
Priority | Critical / High / Medium / Low — agreed with Product Owner.
Source | BRD / SRS section reference or stakeholder name.
Status | Draft → In Review → Approved or Rejected.
Design Doc Ref | Reference to the corresponding section in the Design Document.
Module / Component | System module or microservice that implements this requirement.
Test Case ID | Linked test case identifier in the test management tool (e.g. TC-001).
Test Type | Unit / Integration / System / Performance / Security / UI / Compliance.
Test Status | Latest execution status of the linked test case.
Build / Sprint | Sprint or release build where this was implemented and tested.
UAT Case ID | Linked UAT scenario identifier.
UAT Status | Status reported by business/QA during UAT.
Defect ID | Defect tracker ticket (e.g. DEF-007). Leave blank if no defects.
Remarks | Free-text notes: blockers, decisions, cross-links, open questions.